## Sheet1
Task
|  | Start: | 2018-01-08 | End : | 2018-03-23 | QUARTER 1
LEGEND | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Keyword | Color | Key Milestone #1: Mechanical Prototypes
Planned | planned | Weekly Milestone #1: Planning |  |  |  | QUARTER 1 3: complete
Complete | complete | Weekly Milestone #2: Designing |  |  |  | QUARTER 1 3: complete
Behind | behind | Weekly Milestone #3: CAD |  |  |  | QUARTER 1 4: complete
|  | Weekly Milestone #4: Build |  |  |  | QUARTER 1 5: complete
|  | Weekly Milestone #5: Reiterate |  |  |  | QUARTER 1 6: planned
Key Milestone #2: Ongoing Documentation
|  | Weekly Milestone #1: Project Webpresence |  |  |  | QUARTER 1 5: planned
Key Milestone #3: Analyze and Process Images
|  | Weekly Milestone #1: Image Capture |  |  |  | QUARTER 1 3: complete
|  | Weekly Milestone #2: Isolate Pad from Non-Pad Area |  |  |  | QUARTER 1 4: complete
|  | Weekly Milestone #3: Soil Level |  |  |  | QUARTER 1 5: complete
|  | Weekly Milestone #4: Analyzing Pad |  |  |  | QUARTER 1 6: planned
|  | Weekly Milestone #5: Detecting Presence of Dog |  |  |  | QUARTER 1 8: planned
Key Milestone #4 [Extra]: Communicate with Brilliant Pad
|  | Weekly Milestone #1: Send a signal to the Brilliant Pad |  |  |  | QUARTER 1 7: planned
|  | Weekly Milestone #2: Integrate Vision System with Brilliant Pad |  |  |  | QUARTER 1 9: planned